## MODI Project Tracker
📊 MODI PROJECT - WORKING TRACKER
Medical OPD Digital Interface ¦ Nov 2025 - Dec 2025 ¦ Updated: 15-Dec-2025
Sr# | 📁 Module/File | 📝 Description | 📅 Start | 📅 End | ⏱️ Hrs | 📊 Status | ⚡ Priority | 📌 Notes
1 | main.dart | App Entry Point & Routing | 01-Nov-2025 | 02-Nov-2025 | 4 | ✅ COMPLETE | HIGH | Theme & navigation setup
2 | splash_screen.dart | Animated Splash Screen | 02-Nov-2025 | 03-Nov-2025 | 6 | ✅ COMPLETE | MEDIUM | Custom logo animations
3 | login_signup_choice.dart | Login/Signup Selection | 03-Nov-2025 | 05-Nov-2025 | 8 | ✅ COMPLETE | HIGH | Role-based options
4 | doctor_login_page.dart | Doctor Login Auth | 05-Nov-2025 | 07-Nov-2025 | 10 | ✅ COMPLETE | HIGH | Secure validation
5 | staff_login_page.dart | Staff Login Page | 07-Nov-2025 | 08-Nov-2025 | 6 | ✅ COMPLETE | HIGH | OPD staff auth
6 | doctor_registration_page.dart | Doctor Registration | 08-Nov-2025 | 12-Nov-2025 | 16 | ✅ COMPLETE | HIGH | Multi-step form
7 | doctor_dashboard.dart | Main Doctor Dashboard | 12-Nov-2025 | 25-Nov-2025 | 40 | ✅ COMPLETE | CRITICAL | Full analytics dashboard
8 | opd_staff_dashboard.dart | Staff Dashboard | 20-Nov-2025 | 30-Nov-2025 | 35 | ✅ COMPLETE | CRITICAL | Patient queue mgmt
9 | patient_registration_form.dart | Patient Registration | 25-Nov-2025 | 02-Dec-2025 | 30 | ✅ COMPLETE | CRITICAL | Photo & validation
10 | patient_detail_view.dart | Patient Details View | 01-Dec-2025 | 08-Dec-2025 | 32 | ✅ COMPLETE | HIGH | Medical history view
11 | consultation_screen.dart | Doctor Consultation | 02-Dec-2025 | 06-Dec-2025 | 18 | ✅ COMPLETE | HIGH | Diagnosis & Rx
12 | prescription_page.dart | Prescription Generation | 04-Dec-2025 | 07-Dec-2025 | 12 | ✅ COMPLETE | HIGH | PDF prescription
13 | payment_management.dart | Payment System | 05-Dec-2025 | 08-Dec-2025 | 20 | ✅ COMPLETE | HIGH | Multi-mode payments
14 | payment_installment_screen.dart | Installment Management | 06-Dec-2025 | 10-Dec-2025 | 24 | ✅ COMPLETE | MEDIUM | EMI tracking
15 | database_helper.dart | SQLite Database Layer | 01-Nov-2025 | 10-Dec-2025 | 50 | ✅ COMPLETE | CRITICAL | All CRUD operations
16 | models.dart | Data Models | 01-Nov-2025 | 10-Nov-2025 | 15 | ✅ COMPLETE | HIGH | Patient/Doctor/Staff
17 | patient_qr_code.dart | QR Code Generation | 08-Dec-2025 | 12-Dec-2025 | 18 | ✅ COMPLETE | MEDIUM | Deep link QR
18 | waiting_room_display.dart | TV Display Queue | 10-Dec-2025 | 14-Dec-2025 | 22 | ✅ COMPLETE | MEDIUM | Large screen
19 | whatsapp_integration.dart | WhatsApp Messaging | 08-Dec-2025 | 12-Dec-2025 | 16 | ✅ COMPLETE | MEDIUM | Patient notifications
20 | sms_integration.dart | SMS Service | 09-Dec-2025 | 12-Dec-2025 | 14 | ✅ COMPLETE | MEDIUM | Bulk SMS
21 | birthday_notification_widget.dart | Birthday Reminders | 08-Dec-2025 | 10-Dec-2025 | 10 | ✅ COMPLETE | LOW | Auto birthday wishes
22 | reports_analytics.dart | Analytics Dashboard | 06-Dec-2025 | 10-Dec-2025 | 18 | ✅ COMPLETE | MEDIUM | Revenue charts
23 | settings_configuration.dart | App Settings | 05-Dec-2025 | 10-Dec-2025 | 16 | ✅ COMPLETE | MEDIUM | Clinic config
24 | pdf_service.dart | PDF Generation | 04-Dec-2025 | 08-Dec-2025 | 20 | ✅ COMPLETE | HIGH | Invoices & Rx
25 | design_system.dart | UI Design System | 01-Nov-2025 | 15-Nov-2025 | 12 | ✅ COMPLETE | HIGH | Colors/fonts/themes
26 | responsive_helper.dart | Responsive Layouts | 10-Nov-2025 | 15-Nov-2025 | 10 | ✅ COMPLETE | MEDIUM | Mobile/Desktop
27 | glassmorphism.dart | Glass UI Effects | 12-Nov-2025 | 14-Nov-2025 | 6 | ✅ COMPLETE | LOW | Modern UI styling
28 | appointment_management.dart | Appointment System | 01-Dec-2025 | 06-Dec-2025 | 14 | ✅ COMPLETE | HIGH | Booking & scheduling
29 | book_appointment.dart | Appointment Booking | 02-Dec-2025 | 05-Dec-2025 | 12 | ✅ COMPLETE | HIGH | Patient booking UI
30 | follow_up_appointments.dart | Follow-up Tracking | 05-Dec-2025 | 08-Dec-2025 | 10 | ✅ COMPLETE | MEDIUM | Auto reminders
31 | patient_search.dart | Patient Search | 28-Nov-2025 | 02-Dec-2025 | 12 | ✅ COMPLETE | HIGH | Name/Mobile/QR
32 | notifications_center.dart | Notification Hub | 06-Dec-2025 | 10-Dec-2025 | 10 | ✅ COMPLETE | MEDIUM | Central alerts
33 | medicine_database.dart | Medicine Catalog | 01-Dec-2025 | 06-Dec-2025 | 18 | ✅ COMPLETE | MEDIUM | Drug database
34 | staff_management.dart | Staff CRUD | 25-Nov-2025 | 30-Nov-2025 | 12 | ✅ COMPLETE | MEDIUM | Staff accounts
35 | indian_festival_calendar.dart | Festival Calendar | 08-Dec-2025 | 10-Dec-2025 | 6 | ✅ COMPLETE | LOW | Holiday planning
36 | patient_feedback_system.dart | Feedback QR | 14-Dec-2025 | 14-Dec-2025 | 4 | ✅ COMPLETE | LOW | Google Form QR
37 | forgot_password_page.dart | Password Reset | 08-Nov-2025 | 10-Nov-2025 | 8 | ✅ COMPLETE | HIGH | Email reset flow
38 | advertisement_page.dart | Clinic Ads Display | 10-Dec-2025 | 12-Dec-2025 | 10 | ✅ COMPLETE | LOW | Promotional content
39 | patient_report_page.dart | Patient Report View | 12-Dec-2025 | 14-Dec-2025 | 8 | ✅ COMPLETE | MEDIUM | Web-based report
40 | voice_prescription.dart | Voice Input | 04-Dec-2025 | - | 6 | ⏳ PENDING | LOW | Speech to text
41 | lab_reports_management.dart | Lab Reports | 10-Dec-2025 | - | 8 | ⏳ PENDING | MEDIUM | Report uploads
42 | email_service.dart | Email Integration | 08-Dec-2025 | 10-Dec-2025 | 6 | ✅ COMPLETE | MEDIUM | SMTP service
43 | 🔮 Multi-clinic Support | Multiple Branches | - | - | - | ⏳ PENDING | HIGH | Future enhancement
44 | 🔮 Inventory Management | Medicine Stock | - | - | - | ⏳ PENDING | MEDIUM | Future enhancement
45 | 🔮 Insurance Integration | Claim Processing | - | - | - | ⏳ PENDING | LOW | Future enhancement
📈 PROJECT SUMMARY |  |  |  |  | 609 HRS | 40✅ ¦ 5⏳ | 88.9% COMPLETE